## Sheet1
No. | Task | Began | Completed | Tested | Git Backup Made?
2 | Build Top Level: GA attempt 2
2.1 | New design idea | 2017-02-18 | 2017-02-20 | - | N
2.2 | Fittness Function | 2017-02-20 | 2017-02-21 | Y | Y
2.3 | Selection Roulette Wheel | 2017-02-21 | 2017-02-22 | Y | Y
2.4 | Crossover | 2017-02-22 | 2017-02-23 | Y | Y
2.5 | Mutation | 2017-02-23 | 2017-02-23 | Y | Y
2.6 | Test whole EA | 2017-02-24 | 2017-02-25 | SHEET 2
2.6.1 | Bug with calculating Largest fitness and locus rangeing | 2017-02-26 | 2017-02-26
2.6.2 | Major Error found - fitness not converging to the max, implemented elitism to fix | 2017-02-28 | 2017-03-01
2.7 | Writing test benches for EA | 2017-03-03
2.7.1 | automaticaly converting decimal input to binary string representation | 2017-03-03
2.7.2 | bug with interger to binary mapping occurred |  |  | SHEET 3
Turns out need to use float encoding

## Sheet2
[5 empty] | Key: | Good | Bad
GA2 Test Results
| TEST Set : | Checking Completed EA2 | Test No. : 1 | ID:
| Gen 1 | Gen 2 | Gen 3 | Gen 4 | Gen 5 | Gen 6 | Gen 7 | Gen 8 | Gen 9 | Gen 10 | Final
| 1 0 1 0 | 1 0 1 0 | 1 1 0 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 0 | 1 1 1 1
| 1 0 0 0 | 1 0 0 0 | 0 1 1 0 | 1 0 1 0 | 1 0 0 1 | 0 1 1 1 | 1 0 1 1 | 1 0 1 0 | 0 1 0 1 | 0 1 1 0 | 1 1 1 1
| 0 0 1 1 | 1 0 0 0 | 0 1 1 0 | 1 0 1 0 | 0 0 1 1 | 1 0 1 0 | 1 1 1 0 | 1 1 1 1 | 0 0 0 1 | 0 0 0 0 | 1 0 0 0
| 1 1 0 0 | 1 0 1 1 | 1 1 1 0 | 0 0 0 1 | 1 0 0 1 | 0 1 1 1 | 1 1 1 0 | 0 1 0 1 | 1 0 1 0 | 0 1 1 1 | 1 0 1 0
| 0 1 1 1 | 1 0 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 0 0 1 1 | 1 0 1 0 | 0 0 0 1 | 0 0 0 1 | 0 0 0 0 | 0 0 1 0
| 1 0 0 0 | 0 1 0 1 | 0 0 0 0 | 0 0 0 1 | 0 0 0 0 | 0 0 0 0 | 0 0 1 0 | 0 0 0 1 | 0 0 0 0 | 0 0 0 0 | 0 0 0 0
| 3.75 | 4 | 4.5 | 4.5 | 4.5 | 4.5 | 5 | 4.5 | 3.5 | 3 |  | :Manual averaging calculations for checking
| 5 | 6 | 6 | 5 | 6 | 6 | 7 | 6 | 5 | 4 |  | :Manual Largest Fitness checking
Reasons for test:
Test the graphical display of fitness each generation
Conclusion:
We can see that the graph is mapping correctly the average fitness (blue)
But there is a bug with the largest fitness (green) two values are wrong
Test Improvements needed:
Need to put a key onto the graph to distinguish the meaning of both the lines
Need to take multiple tests and look at the average
intreasted to see how the minimum fitness changes too
Resulting Software improvments:
key added to graph
minimum fitness line added to graph
| TEST Set : | Checking Completed EA2 | Test No. : 1 | ID:
| Gen 1 | Gen 2 | Gen 3 | Gen 4 | Gen 5 | Gen 6 | Gen 7 | Gen 8 | Gen 9 | Gen 10 | Final
| 1 1 0 1 | 0 1 0 1 | 0 0 0 0 | 0 0 1 0 | 0 0 0 0 | 0 0 0 0 | 1 0 0 0 | 1 0 1 0 | 1 1 0 1 | 1 1 1 1 | 1 1 1 1
| 0 0 0 0 | 1 0 1 0 | 1 1 1 1 | 1 1 1 1 | 1 0 1 1 | 0 1 0 1 | 0 1 0 0 | 1 0 0 1 | 0 1 0 1 | 0 1 0 1 | 0 1 0 1
| 1 1 0 1 | 0 0 0 1 | 1 0 0 0 | 0 1 0 1 | 0 0 1 0 | 0 1 0 1 | 0 0 1 1 | 0 0 0 0 | 1 1 0 0 | 1 1 1 1 | 1 1 1 1
| 0 0 1 0 | 1 0 1 0 | 1 0 1 0 | 1 0 0 0 | 0 1 1 0 | 0 0 1 1 | 1 0 1 0 | 1 1 0 0 | 1 0 1 0 | 0 0 0 1 | 1 1 0 1
| 0 1 1 0 | 0 1 0 0 | 0 0 1 0 | 1 1 0 0 | 1 1 1 1 | 1 1 1 0 | 1 1 1 1 | 1 0 1 1 | 1 1 1 0 | 1 0 0 1 | 1 0 1 1
| 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 0 1 | 0 1 0 1 | 1 0 0 0 | 1 0 1 0 | 0 1 0 0 | 1 0 1 0
| 4.25 | 4 | 4 | 4.5 | 4.5 | 4 | 4 | 3.5 | 4.5 | 4.5 |  | :Manual averaging calculations for checking
| 5 | 4 | 5 | 5 | 6 | 5 | 4 | 6 | 6 | 6 |  | :Manual Largest Fitness checking
Test 3 | TEST Set : Gen 1: Found the cause of the bug
Test 4 | TEST Set : Gen 1: Bug Fixed with a if statement
| Gen 1 | Gen 2 | Gen 3 | Gen 4 | Gen 5 | Gen 6 | Gen 7 | Gen 8 | Gen 9 | Gen 10 | Final
Test 5 | Bug Fixed with a if statement Gen 1: Intresting result from removing the mutation function
| Gen 1 | Gen 2 | Gen 3 | Gen 4 | Gen 5 | Gen 6 | Gen 7 | Gen 8 | Gen 9 | Gen 10 | Final
| 1 0 0 1 | 0 1 0 1 | 1 0 1 0 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1
| 1 0 1 1 | 0 1 0 1 | 1 0 1 0 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1
| 1 1 0 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1
| 1 0 1 0 | 1 0 1 0 | 1 0 1 0 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1
| 1 0 1 0 | 1 0 1 0 | 1 0 1 0 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1 | 1 1 1 1
| 0 1 0 0 | 0 1 0 1 | 0 1 0 1 | 0 0 0 0 | 0 0 0 0 | 0 0 0 0 | 0 0 0 0 | 0 0 0 0 | 0 0 0 0 | 0 0 0 0 | 0 0 0 0

## Sheet3
Issue: | Using num2bin and bin2num, produces and uses binary representation with no spaces,